{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["已调整"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"已调整","index":0,"n_rows":86,"n_cols":18,"rows_kept":86,"merged":[[0,0,0,1],[1,0,1,17],[2,0,2,4],[2,14,2,17],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,3,8],[3,9,4,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,3,15],[3,16,4,16],[3,17,4,17],[5,0,5,1]],"flags":["formulas_cached_only"]}
["附件"]
["嘉峪关市2018年重点投资项目（调整）清单"]
[{"$nulls":14},"单位：万元"]
["序号","项目名称","主要建设规模","总投资","2018年计划投资","年度计划投资分季度完成投资安排",{"$nulls":3},"计划新开工项目开工月份","进入统计局统计库月份（","项目单位及责任人","省直\n行业\n主管\n部门","包抓政府领导及职务",null,null,"省发改委催办处室","备注（民间投资或PPP）"]
[{"$nulls":5},"一季度（1-3月）完成投资","二季度（1-6月）完成投资","三季度（1-9月）完成投资","四季度\n（1-12月）完成投资",{"$nulls":4},"省政府","市（州）政府","县（市区）政府"]
["合计（48项）",null,null,2685002,1144606,87500,451212,895502,1138246]
["一","续建项目（20项）",null,1030870,380240,57500,215212,321102,376880]
["（一）","农林牧渔（**项）",{"$nulls":14},"农经处"]
["（二）","交通（1项）",null,29000,17000,3000,8000,13000,17000]
[1,"G312线嘉峪关至清泉段","新建嘉峪关境内二级公路44公里",29000,17000,3000,8000,13000,17000,null,null,"交通局\n程  仁","省交通厅",null,"赵宝毅\n副市长",null,"交通处"]
["（三）","水利（**项）",{"$nulls":14},"农经处"]
["（四）","能源（**项）",{"$nulls":14},"电力处、新能源处、煤油处、管道处"]
["（五）","社会事业（8项）",null,422718,164188,37500,128212,152050,160828]
[1,"嘉峪关丝绸之路文化博览园项目","建设丝路、长城等文化为创意基础的主题体验园区",310000,102712,30000,102712,102712,102712,null,null,"文旅集团\n齐新民","省旅游委",null,"义战鹰\n副市长",null,"社会处"]
[2,"世界文化遗产公园--花博园","占地面积40万平方米，一期实施场地平整及绿化种植工程",16932,4500,500,2000,4500,4500,null,null,"大景区管委会\n赵金山","省旅游委",null,"义战鹰\n副市长",null,"社会处"]
[3,"关城大景区停车场","总建筑面积43676.31平方米",15478,9478,1000,5000,8000,9478,null,null,"大景区管委会\n赵金山","省旅游委",null,"义战鹰\n副市长",null,"社会处"]
[4,"长城博物馆项目","总建筑面积9979平方米",12010,4338,0,2000,4338,4338,null,null,"大景区管委会\n赵金山","省旅游委",null,"义战鹰\n副市长",null,"社会处"]
[5,"嘉峪关市第一人民医院建设项目（一期）和儿童专科病区医疗辅属专项配套工程","实施医疗净化、实验室、医疗污废水处理等工程",18800,16300,3000,7000,14000,16300,null,null,"卫计委\n徐红岩","省卫计委",null,"赵宝毅\n副市长",null,"社会处"]
[6,"嘉峪关市怡心苑康复医养养老中心新建及改造项目","建设面积34800平方米",30000,20000,3000,8000,15000,20000,null,null,"民政局\n史有峰","省民政厅",null,"赵宝毅\n副市长",null,"社会处"]
[7,"酒钢医院危旧门诊综合楼改扩建项目","总建筑面积28000平方米",10000,3500,0,1500,3500,3500,null,null,"卫计委\n徐红岩","省卫计委",null,"赵宝毅\n副市长",null,"社会处"]
[8,"世界文化遗产保护与展示工程—遗产监测中心项目","新建遗产监测中心一栋，总建筑面积8460平方米，地上一层，局部地下一层，主要有监测中心、监测办公室、展览大厅、会议室、研究室、监测站等，并配套建设给排水、暖通、电气、消防、绿化等附属设施",9498,3360,{"$nulls":6},"大景区管委会\n赵金山","省旅游委",null,"义战鹰\n副市长",null,"社会处","新增"]
["（六）","城建（1项）",null,10152,2152,0,1000,2152,2152]
[1,"棚户区迎宾路提升改造工程","改造道路总长5374米",10152,2152,0,1000,2152,2152,null,null,"建设局\n侯金森","省住建厅",null,"何正义\n副市长",null,"投资处"]
["（七）","工业（3项）",null,281000,76000,11000,33000,56000,76000]
[1,"多功能专用汽车生产项目","建设年产10万辆多功能整车汽车生产基地及配套服务设施",200000,50000,5000,20000,35000,50000,null,null,"工业园区\n丁南江","省发改委",null,"赵宝毅\n副市长",null,"产业处"]
[2,"中核嘉华核技术产业园","建设备品备件加工、核容器生产、压力容器设计、制造等为一体的核技术产业园",53000,3000,0,1000,3000,3000,null,null,"工业园区\n丁南江","省发改委",null,"赵宝毅\n副市长",null,"产业处"]
[3,"不锈钢铬钢酸洗线建设项目","建设主厂房、铬钢酸洗设备，配套供配电、电器系统及计算机控制系统等",28000,23000,6000,12000,18000,23000,null,null,"工信委\n安维国","省工信委",null,"赵宝毅\n副市长",null,"产业处"]
["（八）","高技术和信息化（**项）",{"$nulls":14},"高技术处"]
["（九）","生态环保（1项）",null,16000,5000,0,1000,4000,5000]
[1,"嘉峪关市第二污水处理厂建设工程（先期）","新建污水收集管网22.4公里和1000立方米/日的污水提升泵站一座",16000,5000,0,1000,4000,5000,null,null,"建设局\n侯金森","省住建厅",null,"何正义\n副市长",null,"资环处"]
["（十）","对外开放（**项）",{"$nulls":14},"西开办、外资处"]
["（十一）","经贸物流（2项）",null,67000,40000,4000,18000,32000,40000]
[1,"国泰大酒店有限公司嘉丰源大厦","总建筑面积69600平方米",36000,15000,2000,8000,12000,15000,null,null,"商务局\n李向东","省商务厅",null,"赵宝毅\n副市长",null,"经贸处","民间投资"]
[2,"紫轩国际","总建筑面积50000平方米",31000,25000,2000,10000,20000,25000,null,1,"商务局\n李向东","省商务厅",null,"赵宝毅\n副市长",null,"经贸处","民间投资"]
["（十二）","扶贫开发（**项）",{"$nulls":14},"代赈办"]
["（十三）","社会管理（**项）",{"$nulls":14},"待定"]
["（十四）","房地产开发（4项）",null,205000,75900,2000,26000,61900,75900]
[1,"嘉峪关市润泽公馆商品住宅楼项目","新建润泽公馆商品住宅及商业综合楼48栋，总建筑面积199703平方米，分六期实施",80000,38000,null,10000,30000,38000,null,null,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","新增"]
[2,"远东华府住宅小区","新建远东华府住宅小区商品住宅楼32栋，总建筑面积201500平方米",81000,25000,null,9000,20000,25000,null,null,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","新增"]
[3,"嘉峪关市雍平街区棚户区改造项目1-5期","32栋6层住宅，总建筑面积14.1万平方米",32000,4900,1000,3000,4900,4900,null,null,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处"]
[4,"嘉峪关市雍平街区棚户区改造项目六期（1标段）","2栋18层住宅，1栋7层住宅，4.6万平方米",12000,8000,1000,4000,7000,8000,null,null,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处"]
["（十五）","其他（**项）",{"$nulls":14},"待定"]
["二","计划新开工项目（28项）",null,1654132,764366,30000,236000,574400,761366]
["（一）","农林牧渔（2项）",null,114100,37000,0,11000,30000,37000]
[1,"镜铁区戈壁现代农业示范园建设项目\n","主要建设嘉峪关晨翔阳光农业科技生态园项目、甘肃鲁农戈壁农业示范园、嘉峪关东塘生态循环农业产业园、丰源农业科技示范园项目、嘉峪关百汇农业科技生态园项目、嘉峪关万合春现代农业示范园项目及相关配套工程",99100,30000,0,10000,25000,30000,null,null,"镜铁区\n侯金芳","省农牧厅",null,"马东彦\n副市长",null,"农经处","新增"]
[2,"新城镇戈壁农业发展园区项目","新建新城戈壁农业发展园区，修建日光温室50座，完善基础设施",15000,7000,0,1000,5000,7000,5,6,"长城区\n景光耀","省农牧厅",null,"马东彦\n副市长",null,"农经处"]
["（二）","交通（1项）",null,18127,5000,0,1000,3000,5000]
[1,"驻嘉68217部队至68208装甲部队训练场（祁丰区嘉峪关段）","新建三级公路33公里",18127,5000,0,1000,3000,5000,6,6,"交通局\n程  仁","省交通厅",null,"赵宝毅\n副市长",null,"交通处"]
["（三）","水利（**项）",{"$nulls":14},"农经处"]
["（四）","能源（**项）",{"$nulls":14},"电力处、新能源处、煤油处、管道处"]
["（五）","社会事业（4项）",null,156385,53000,0,17000,40000,53000]
[1,"峪泉古街","项目规划面积为434亩，建设内容为恢复历史古街、打造具有明清风格、体现丝路文化和河西风情的公馆、茶楼、酒肆、商铺、民宅、市场、口岸、戏台等街区廊坊等，业态包括旅游观光、娱乐演艺、休闲度假、文化体验、情景商业、主题酒店、客栈与民宿、后勤配套用房等",100000,30000,0,10000,22000,30000,null,null,"嘉峪关文旅集团\n齐新民","省旅游委",null,"义战鹰\n副市长",null,"社会处","新增"]
[2,"嘉峪关世界文化遗产保护与展示工程区域架空线路入地改造项目","新建电缆5.6公里",26385,12000,0,4000,9000,12000,4,5,"嘉峪关大景区管委会\n赵金山","省旅游委",null,"义战鹰\n副市长",null,"社会处"]
[3,"关城大景区湿地恢复及景观水面改造","遗产公园内原湿地改造、新增湿地及水系连通工程",11000,6000,0,2000,5000,6000,5,6,"嘉峪关大景区管委会\n赵金山","省旅游委",null,"义战鹰\n副市长",null,"社会处"]
[4,"关城大景区园区基础设施建设项目","实施环境整治及绿化种植区域面积约为99.3万平方米及配套基础设施",19000,5000,0,1000,4000,5000,5,6,"嘉峪关大景区管委会\n赵金山","省旅游委",null,"义战鹰\n副市长",null,"社会处"]
["（六）","城建（3项）",null,66171,66171,0,19000,49000,66171]
[1,"棚户区道路改造提升工程","改造7条道路、16.9公里",25829,25829,0,10000,20000,25829,4,5,"建设局\n侯金森","省住建厅",null,"何正义\n副市长",null,"投资处"]
[2,"嘉峪关市棚户区道路（建设路、朝阳路、雄关路、钢城路、富强路、五一路）地下管线及附属设施改造工程","对嘉峪关市建设路、朝阳路、雄关路、钢城路、富强路、五一路6条棚户区道路地下给排水、燃气、供热、供电等系统进行改造，改造管线总长10.7公里",27792,27792,null,6000,20000,27792,3,5,"建设局\n侯金森","省住建厅",null,"何正义\n副市长",null,"投资处","新增"]
[3,"城市地下管网建设工程（四期）","改造管网57公里",12550,12550,0,3000,9000,12550,4,5,"建设局\n侯金森","省住建厅",null,"何正义\n副市长",null,"投资处"]
["（七）","工业（5项）",null,822100,336000,30000,123000,258000,333000]
[1,"年产20万吨高精度交通用铝板项目","新建办公楼、生产车间等公辅设施，购置设备",500000,100000,0,20000,60000,100000,5,6,"工信委\n安维国","省工信委",null,"赵宝毅\n副市长",null,"产业处","民间投资"]
[2,"酒钢产业升级项目（打捆）","酒钢产业升级项目",260000,220000,30000,100000,190000,220000,3,4,"工信委\n安维国","省工信委",null,"赵宝毅\n副市长",null,"产业处"]
[3,"酒钢本部7号高炉系统优化改造项目","炉型重新设计、铁口重新布局、炉内冷却设施、耐材更新",34900,5000,0,1000,3000,5000,5,6,"工信委\n安维国","省工信委",null,"赵宝毅\n副市长",null,"产业处"]
[4,"双面埋弧焊接螺旋钢管、预制直埋聚氨酯保温钢管及PE缠绕复合钢管项目","新建生产车间、办公楼及其它一些辅助设施，购进双面埋弧焊接螺旋管生产机组2套；预制直埋保温钢管生产线2套，发泡机组2台，PE缠绕生产机组 1 套等设备，购进后建设双面埋弧螺旋钢管生产线2条，预制直埋保温管生产线2条，PE缠绕复合钢管生产线1条",8000,6000,0,2000,4000,6000,null,null,"工信委\n安维国","省工信委",null,"赵宝毅\n副市长",null,"产业处","新增"]
[5,"装配式建筑智能制造产业基地","新建办公研发楼、孵化基地、建筑大数据信息中心、装配式培训教育基地、商务中心、宿舍餐饮楼、装配式研发中试车间、PC装配式生产厂房、模具加工厂房、装配式门窗厂厂房、钢结构装配式生产厂房、硅酸钙板生产厂房、装配式装饰保温一体板生产车间、装配式轻质内隔墙板生产车间、混凝土生产车间及原料仓储库房、成品堆场、锅炉房及管道、公厕、配套道路、绿化、给排水、消防通风、电气等工程",19200,5000,0,null,1000,2000,6,7,"工信委\n安维国","省工信委",null,"赵宝毅\n副市长",null,"产业处","新增"]
["（八）","高技术和信息化（项）"]
["（九）","生态环保（2项）",null,43961,32695,0,6000,23400,32695]
[1,"草湖国家湿地公园建设项目","启动湿地保育区和恢复重建区生态建设；完成湿地公园服务区建设",23961,22695,0,3000,16000,22695,5,5,"农林局\n龚雪爱","省农牧厅",null,"马东彦\n副市长",null,"农经处"]
[2,"嘉北污水处理厂及管网建设项目","建设一座处理嘉北区域生活和工业污水设计规模3.5万立方米/日污水处理厂及配套的管网等",20000,10000,null,3000,7400,10000,3,4,"润源公司\n李志磊","省发\n改委",null,"何正义\n副市长",null,"资环处","新增"]
["（十）","对外开放（**项）",{"$nulls":14},"西开办、外资处"]
["（十一）","经贸物流（2项）",null,38000,24000,0,4000,18000,24000,{"$nulls":7},"经贸处"]
[1,"万豪国际","建设万豪国际广场及配套设施，总建筑面积79000平方米",26000,20000,0,3000,15000,20000,6,7,"商务局\n李向东","省商务厅",null,"赵宝毅\n副市长",null,"经贸处","民间投资"]
[2,"西部天地物流配送中心项目","总占地面积31800平方米",12000,4000,0,1000,3000,4000,6,7,"国际港务区管委会\n刘  鹏","省商务厅",null,"赵宝毅\n副市长",null,"经贸处","民间投资"]
["（十二）","扶贫开发（**项）",{"$nulls":14},"代赈办"]
["（十三）","社会管理（**项）",{"$nulls":14},"待定"]
["（十四）","房地产开发（9项）",null,395288,210500,0,55000,153000,210500,{"$nulls":7},"投资处"]
[1,"嘉峪关市2018年棚户区改造（二期）项目","对城市老旧小区和城市危房进行改造，改造套数12189套",60788,20000,0,0,10000,20000,9,10,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","新增"]
[2,"中天置业房地产开发项目","在酒泉、张掖开发建设住宅楼，总建筑面积80000平方米",38000,25000,0,10000,20000,25000,3,4,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","新增"]
[3,"雍平街棚户区改造项目六期工程","建设高层及商业设施，总建筑面积29万平方米",80000,50000,0,10000,30000,50000,5,6,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处"]
[4,"建安、建林等街区棚户区改造项目","继续实施建安、建林棚户区改造后续工程",60000,30000,0,8000,25000,30000,5,6,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处"]
[5,"金色海岸住宅工程","总建筑面积83500平方米",45500,21500,0,5000,18000,21500,5,6,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","民间投资"]
[6,"嘉峪关市南湖鑫港住宅小区 ","总建筑面积72900平方米",25000,25000,0,8000,18000,25000,5,6,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","民间投资"]
[7,"天诚·尚品Class","总建筑面积150000平方米",21000,21000,0,8000,18000,21000,5,6,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","民间投资"]
[8,"爱嘉庭院二期","新建住宅楼7栋，总建筑面积43633平方米",13000,13000,0,5000,10000,13000,5,6,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处","民间投资"]
[9,"文旅别院","总建筑面积262000平方米",52000,5000,0,1000,4000,5000,5,6,"房管局\n陈学军","省住建厅",null,"何正义\n副市长",null,"投资处"]
["（十五）","其他（**项）",{"$nulls":14},"待定"]